## Sheet1
No. | Task Name | Task Items | Task Type | Task Status | Resource | Start Date | Completed Date | Target Date | Comments
1 | Angular code base structuring |  | Frontend | In Progress | Abhiram | 2022-10-05
2 | Landing Page | Component creation | Frontend | In Progress | Abhiram | 2022-10-07
|  | Add new (dashboard) | Frontend |  | Abhiram
|  | Create new (engagement, dashboard) | Frontend |  | Abhiram
|  | Page design | Frontend |  | Abhiram
|  | UI integration | Frontend |  | Abhiram
3 | Navigation bar | Component creation | Frontend |  | Abhiram
|  | Design | Frontend |  | Abhiram
|  | Search | Frontend |  | Abhiram
|  | UI integration | Frontend |  | Abhiram
4 | Side bar | Component creation | Frontend |  | Abhiram
|  | Expand/collapse | Frontend |  | Abhiram
|  | Search | Frontend |  | Abhiram
|  | Design | Frontend |  | Abhiram
|  | UI integration | Frontend |  | Abhiram
5 | Dashboard cards | Component creation | Frontend |  | Abhiram
|  | Edit/configure | Frontend |  | Abhiram
|  | Refresh | Frontend |  | Abhiram
|  | Alerts (view/edit) | Frontend |  | Abhiram
|  | Export | Frontend |  | Abhiram
|  | UI integration | Frontend |  | Abhiram
6 | Structure Database | Create and structure tables | Backend |  | Vineesh
7 | Create basic application structure |  | Backend | In Progress | Vineesh | 2022-10-06
8 | Fetch data from database |  | Backend |  | Vineesh
9 | Save data to database |  | Backend |  | Vineesh
10 | Create engagement | Form component creation | Frontend |  | Abhiram
|  | Form design | Frontend |  | Abhiram
|  | Create alert | Frontend |  | Abhiram
|  | Save data to database | Backend |  | Vineesh
11 | View Engagement | Fetch data from DB | Backend |  | Vineesh
|  | Display engagement details | Frontend |  | Abhiram
12 | Edit Engagement | Show engagement configurations | Frontend |  | Abhiram
|  | Save changes to DB | Backend |  | Vineesh
13 | Create dashboard | Form component creation | Frontend |  | Abhiram
|  | Form design | Frontend |  | Abhiram
|  | Create alert | Frontend |  | Abhiram
|  | Save data to database | Backend |  | Vineesh
14 | View Dashboard | Fetch data from DB | Backend |  | Vineesh
|  | Display dashboard | Frontend |  | Abhiram
15 | Edit Dashboard | Show dashboard configurations | Frontend |  | Abhiram
|  | Save changes to DB | Backend |  | Vineesh
16 | Create Chart | Form component creation | Frontend |  | Abhiram
|  | Save data to database | Backend |  | Vineesh
|  | Form design | Frontend |  | Abhiram
17 | View Chart | Fetch sample data from sample DB | Backend | Completed | Vineesh | 2022-10-06 | 2022-10-06
|  | Display sample chart | Frontend | Completed | Vineesh | 2022-10-06 | 2022-10-10
|  | Fetch data from DB | Backend |  | Vineesh
|  | Display chart | Frontend |  | Abhiram
18 | Edit Chart | Show chart configurations | Frontend |  | Abhiram
|  | Save changes to DB | Backend |  | Vineesh
19 | User access management | Login Page | Frontend |  | Abhiram
|  | Login function | Backend |  | Vineesh
|  | Store user info in DB | Backend |  | Vineesh
|  | Give specified access for users | Frontend |  | Abhiram
|  | Give specified access for users | Backend |  | Vineesh
|  | Logout function | Backend |  | Vineesh
20 | Deployment frequency backend function |  | Backend |  | Vineesh
21 | Lead time for changes backend function |  | Backend |  | Vineesh
22 | Change failure rate backend function |  | Backend |  | Vineesh
23 | Mean time to recover backend function |  | Backend |  | Vineesh
24 | Create alerts |  | Frontend |  | Abhiram
25 |  |  | Backend |  | Vineesh